## ACTION_LOG
Task ID | Opening Type | Location | Macro Area | Sub Area | Task | Description | Status | Progress % | Owner 1 (Lead) | Owner 2 | Owner 3 | Task Open Date | Due Date | Latest Update | Latest Update Date | Update History | Blocker / Decision | Decision Required | Critical for Opening | Check | Baseline Due Date | Last Modified | Last Modified By
AMS-001 | New Store | Amsterdam Airport | Contract |  | Sign concession agreement with Schiphol | Concession agreement incl. revenue share and fit-out timeline | Completed | 100 | G. Conti |  |  | 2026-03-02 | 2026-06-30 | Countersigned copy archived | 2026-07-02 |  |  | FALSE | TRUE |  | 2026-06-30 | 2026-09-29 09:00 | Demo data
AMS-002 | New Store | Amsterdam Airport | Store Planning |  | Final layout approval by airport authority | Rev. C layout incl. fire exits and storage | In Progress | 50 | L. Bianchi |  |  | 2026-03-16 | 2026-10-17 | Rev. C submitted, feedback expected wk 41 | 2026-09-24 |  |  | FALSE | TRUE |  | 2026-09-30 | 2026-09-29 09:00 | Demo data
AMS-003 | New Store | Amsterdam Airport | HR |  | Airport access passes for store staff | Request passes for SM + 6 SA via Schiphol security | Blocked | 25 | S. Moretti | L. Bianchi |  | 2026-09-15 | 2026-10-15 | Waiting for Schiphol security feedback | 2026-09-29 |  | Pass request needs final staff list; recruitment not closed | FALSE | TRUE |  | 2026-10-15 | 2026-09-29 09:00 | Demo data
AMS-004 | New Store | Amsterdam Airport | HR |  | Recruit store team (SM + 6 SA) |  | In Progress | 75 | S. Moretti |  |  | 2026-07-01 | 2026-10-10 | SM hired; 2 SA offers pending | 2026-09-22 |  |  | FALSE | TRUE |  | 2026-09-30 | 2026-09-29 09:00 | Demo data
AMS-005 | New Store | Amsterdam Airport | IT | POS | POS installation and store code setup |  | Not Started | 0 | M. Ferri |  |  | 2026-09-01 | 2026-11-20 |  |  |  |  | FALSE | TRUE |  | 2026-11-20 | 2026-09-29 09:00 | Demo data
AMS-006 | New Store | Amsterdam Airport | IT | Connectivity | Airside fibre line activation | Only airport-approved providers allowed airside | In Progress | 25 | M. Ferri |  |  | 2026-09-01 | 2026-10-31 | Two airport-approved providers quoted | 2026-09-25 |  | Choose provider: lead time vs cost | TRUE | TRUE |  | 2026-10-31 | 2026-09-29 09:00 | Demo data
AMS-007 | New Store | Amsterdam Airport | Logistics & Customs |  | Define airside delivery and customs regime |  | In Progress | 25 | A. Greco |  |  | 2026-09-10 | 2026-10-24 | Customs broker briefed | 2026-09-19 |  | Duty-free or duty-paid assortment? | TRUE | TRUE |  | 2026-10-24 | 2026-09-29 09:00 | Demo data
AMS-008 | New Store | Amsterdam Airport | Compliance & Labelling |  | Validate NL labelling requirements |  | Not Started | 0 | F. Riva |  |  | 2026-09-01 | 2026-09-25 |  |  |  |  | FALSE | FALSE |  | 2026-09-25 | 2026-09-29 09:00 | Demo data
AMS-009 | New Store | Amsterdam Airport | Finance & Administration |  | Cash handling agreement with airport |  | Completed | 75 | E. Galli |  |  | 2026-07-01 | 2026-09-15 | Agreement signed | 2026-09-12 |  |  | FALSE | FALSE |  | 2026-09-15 | 2026-09-29 09:00 | Demo data
AMS-010 | New Store | Amsterdam Airport | Store Planning |  | Shopfitting completion |  | Not Started | 0 | L. Bianchi |  |  | 2026-09-01 | 2026-12-20 |  |  |  |  | FALSE | TRUE |  | 2026-12-20 | 2026-09-29 09:00 | Demo data
MAD-001 | New Store | Madrid Airport | Contract |  | Sign lease with Aena |  | Completed | 100 | G. Conti |  |  | 2026-02-02 | 2026-04-30 | Signed lease filed | 2026-04-28 |  |  | FALSE | TRUE |  | 2026-04-30 | 2026-09-29 09:00 | Demo data
MAD-002 | New Store | Madrid Airport | Store Planning |  | Shopfitting works |  | In Progress | 75 | L. Bianchi |  |  | 2026-03-02 | 2026-10-23 | Joinery installed; lighting next week | 2026-09-25 |  |  | FALSE | TRUE |  | 2026-10-02 | 2026-09-29 09:00 | Demo data
MAD-003 | New Store | Madrid Airport | IT | POS | POS and payment terminals installation |  | In Progress | 50 | M. Ferri |  |  | 2026-06-01 | 2026-10-16 | Terminals shipped, installation booked 12/10 | 2026-09-24 |  |  | FALSE | TRUE |  | 2026-10-16 | 2026-09-29 09:00 | Demo data
MAD-004 | New Store | Madrid Airport | HR |  | Store team training at HQ |  | Not Started | 0 | S. Moretti |  |  | 2026-07-01 | 2026-10-23 |  |  |  |  | FALSE | FALSE |  | 2026-10-23 | 2026-09-29 09:00 | Demo data
MAD-005 | New Store | Madrid Airport | Allocation & Replenishment |  | First allocation for opening stock |  | In Progress | 25 | D. Serra | R. Marino |  | 2026-08-01 | 2026-10-16 | Draft allocation shared with Retail | 2026-09-23 |  | Confirm opening assortment depth (sizes) | TRUE | TRUE |  | 2026-10-16 | 2026-09-29 09:00 | Demo data
DXB-001 | New Store | Dubai Airport | Corporate / Legal |  | Agreement with duty-free operator |  | Blocked | 50 | C. Villa | G. Conti |  | 2026-03-16 | 2026-09-30 | Operator requests revised revenue share | 2026-09-23 |  | Revenue share not agreed; escalation to Commercial Director | TRUE | TRUE |  | 2026-07-31 | 2026-09-29 09:00 | Demo data
DXB-002 | New Store | Dubai Airport | IT | Connectivity | Network connection via airport provider |  | Not Started | 0 | M. Ferri |  |  | 2026-09-01 | 2026-11-15 |  |  |  |  | FALSE | TRUE |  | 2026-11-15 | 2026-09-29 09:00 | Demo data
DXB-003 | New Store | Dubai Airport | Logistics & Customs |  | Bonded warehouse flow |  | In Progress | 25 | A. Greco |  |  | 2026-07-01 | 2026-10-31 | First call with freight forwarder | 2026-09-10 |  |  | FALSE | TRUE |  | 2026-10-31 | 2026-09-29 09:00 | Demo data
DXB-004 | New Store | Dubai Airport | Compliance & Labelling |  | Arabic labelling compliance |  | Completed | 100 | F. Riva |  |  | 2026-06-01 | 2026-09-15 | Labels approved by operator | 2026-09-11 |  |  | FALSE | FALSE |  | 2026-09-15 | 2026-09-29 09:00 | Demo data
CZE-CO-001 | New Company | Czech Republic | Corporate / Legal |  | Company incorporation (s.r.o.) |  | Completed | 100 | C. Villa |  |  | 2026-05-04 | 2026-07-31 | Registered in Commercial Register | 2026-07-24 |  |  | FALSE | TRUE |  | 2026-07-31 | 2026-09-29 09:00 | Demo data
CZE-CO-002 | New Company | Czech Republic | Finance & Administration |  | Open local bank account |  | In Progress | 50 | E. Galli |  |  | 2026-08-03 | 2026-10-16 | KYC documents submitted to bank | 2026-09-21 |  |  | FALSE | TRUE |  | 2026-10-16 | 2026-09-29 09:00 | Demo data
CZE-CO-003 | New Company | Czech Republic | Finance & Administration |  | VAT registration |  | Not Started | 0 | E. Galli |  |  | 2026-08-03 | 2026-10-30 |  |  |  |  | FALSE | TRUE |  | 2026-10-30 | 2026-09-29 09:00 | Demo data
CZE-CO-004 | New Company | Czech Republic | HR |  | Payroll provider selection |  | In Progress | 25 | S. Moretti | E. Galli |  | 2026-09-01 | 2026-11-06 | Two providers shortlisted | 2026-09-18 |  | Choose between the two shortlisted payroll providers | TRUE | FALSE |  | 2026-11-06 | 2026-09-29 09:00 | Demo data
IST-001 | New Store | Istanbul Airport | Store Planning |  | Layout approval by airport |  | Completed | 100 | L. Bianchi |  |  | 2026-03-02 | 2026-07-31 | Approved by DHMI | 2026-07-29 |  |  | FALSE | TRUE |  | 2026-07-31 | 2026-09-29 09:00 | Demo data
IST-002 | New Store | Istanbul Airport | IT | ERP (SAP) | Create store in SAP (plant, pricing) |  | In Progress | 50 | M. Ferri |  |  | 2026-08-01 | 2026-10-23 | Plant created; pricing conditions pending | 2026-09-24 |  |  | FALSE | TRUE |  | 2026-10-23 | 2026-09-29 09:00 | Demo data
IST-003 | New Store | Istanbul Airport | Indirect Materials |  | Packaging and shopping bags order |  | In Progress | 75 | P. Costa |  |  | 2026-07-01 | 2026-10-09 | Order confirmed, delivery wk 40 | 2026-09-22 |  |  | FALSE | FALSE |  | 2026-10-09 | 2026-09-29 09:00 | Demo data
IST-004 | New Store | Istanbul Airport | Retail |  | Visual merchandising plan |  | Not Started | 0 | R. Marino |  |  | 2026-09-01 | 2026-11-06 |  |  |  |  | FALSE | FALSE |  | 2026-11-06 | 2026-09-29 09:00 | Demo data
KSA-CO-001 | New Company | Saudi Arabia | Corporate / Legal |  | MISA investment license |  | Blocked | 25 | C. Villa |  |  | 2026-03-02 | 2026-10-15 | Second request for documents from MISA | 2026-09-18 |  | Awaiting MISA response on documentation | FALSE | TRUE |  | 2026-06-30 | 2026-09-29 09:00 | Demo data
KSA-CO-002 | New Company | Saudi Arabia | Corporate / Legal |  | Commercial registration (CR) |  | Not Started | 0 | C. Villa | C Villa |  | 2026-03-02 | 2026-11-13 |  |  |  |  | FALSE | TRUE |  | 2026-08-31 | 2026-09-29 09:00 | Demo data

## TASK_HISTORY
History ID | Event Date | Recorded At | Task ID | Entry Type | Note Type | Field | Previous Value | New Value | Note | Author | Source | Session ID | Verification | Check
H-000001 | 2026-09-15 | 2026-09-15 09:10 | AMS-003 | Created | [5 empty] | T. Simoni | App
H-000002 | 2026-09-15 | 2026-09-15 09:12 | AMS-003 | Note | Update |  |  |  | Process started with Schiphol security office | T. Simoni | App
H-000003 | 2026-09-22 | 2026-09-22 10:14 | AMS-003 | Note | Update |  |  |  | Documentation template received from Schiphol | T. Simoni | App | SESSION-20260922-001 | Verified
H-000004 | 2026-09-22 | 2026-09-22 10:20 | AMS-004 | Change |  | Progress % | 50 | 75 |  | T. Simoni | App | SESSION-20260922-001 | Verified
H-000005 | 2026-09-22 | 2026-09-22 10:21 | AMS-004 | Note | Update |  |  |  | SM hired; 2 SA offers pending | T. Simoni | App | SESSION-20260922-001 | Verified
H-000006 | 2026-09-22 | 2026-09-22 10:26 | AMS-002 | Change |  | Due Date | 30/09/2026 | 17/10/2026 |  | T. Simoni | App | SESSION-20260922-001 | Verified
H-000007 | 2026-09-15 | 2026-09-15 16:02 | AMS-002 | Note | Update |  |  |  | Rev. B rejected: storage area too small | T. Simoni | App
H-000008 | 2026-09-24 | 2026-09-24 17:40 | AMS-002 | Note | Update |  |  |  | Rev. C submitted, feedback expected wk 41 | T. Simoni | App
H-000009 | 2026-07-02 | 2026-07-02 11:00 | AMS-001 | Note | Update |  |  |  | Countersigned copy archived | T. Simoni | App
H-000010 | 2026-09-25 | 2026-09-25 12:05 | AMS-006 | Note | Update |  |  |  | Two airport-approved providers quoted | T. Simoni | App
H-000011 | 2026-09-19 | 2026-09-19 15:30 | AMS-007 | Note | Update |  |  |  | Customs broker briefed | T. Simoni | App
H-000012 | 2026-09-12 | 2026-09-12 10:00 | AMS-009 | Note | Update |  |  |  | Agreement signed | T. Simoni | App
H-000013 | 2026-04-28 | 2026-04-28 09:30 | MAD-001 | Note | Update |  |  |  | Signed lease filed | T. Simoni | App
H-000014 | 2026-09-11 | 2026-09-11 14:00 | MAD-002 | Note | Update |  |  |  | Shopfitter on site, works started | T. Simoni | App
H-000015 | 2026-09-22 | 2026-09-22 10:40 | MAD-002 | Change |  | Due Date | 02/10/2026 | 23/10/2026 |  | T. Simoni | App | SESSION-20260922-001 | Verified
H-000016 | 2026-09-25 | 2026-09-25 18:10 | MAD-002 | Note | Update |  |  |  | Joinery installed; lighting next week | T. Simoni | App
H-000017 | 2026-09-24 | 2026-09-24 11:15 | MAD-003 | Note | Update |  |  |  | Terminals shipped, installation booked 12/10 | T. Simoni | App
H-000018 | 2026-09-26 | 2026-09-26 08:55 | MAD-003 | Change |  | Owner 1 (Lead) | A. Greco | M. Ferri | Rilevato nel foglio |  | Sheet
H-000019 | 2026-09-22 | 2026-09-22 10:45 | MAD-005 | Note | Decision |  |  |  | Opening stock to follow Madrid T4 benchmark depth | T. Simoni | App | SESSION-20260922-001 | Verified
H-000020 | 2026-09-23 | 2026-09-23 09:20 | MAD-005 | Note | Update |  |  |  | Draft allocation shared with Retail | T. Simoni | App
H-000021 | 2026-09-09 | 2026-09-09 10:00 | DXB-001 | Note | Update |  |  |  | Draft agreement received from operator | T. Simoni | App
H-000022 | 2026-09-23 | 2026-09-23 16:45 | DXB-001 | Note | Update |  |  |  | Operator requests revised revenue share | T. Simoni | App
H-000023 | 2026-09-29 | 2026-09-29 10:31 | DXB-001 | Change |  | Status | In Progress | Blocked |  | T. Simoni | App | SESSION-20260929-001 | Verified
H-000024 | 2026-09-10 | 2026-09-10 11:00 | DXB-003 | Note | Update |  |  |  | First call with freight forwarder | T. Simoni | App
H-000025 | 2026-09-11 | 2026-09-11 09:00 | DXB-004 | Note | Update |  |  |  | Labels approved by operator | T. Simoni | App
H-000026 | 2026-07-24 | 2026-07-24 12:00 | CZE-CO-001 | Note | Update |  |  |  | Registered in Commercial Register | T. Simoni | App
H-000027 | 2026-09-21 | 2026-09-21 15:00 | CZE-CO-002 | Note | Update |  |  |  | KYC documents submitted to bank | T. Simoni | App
H-000028 | 2026-09-18 | 2026-09-18 10:30 | CZE-CO-004 | Note | Update |  |  |  | Two providers shortlisted | T. Simoni | App
H-000029 | 2026-07-29 | 2026-07-29 09:00 | IST-001 | Note | Update |  |  |  | Approved by DHMI | T. Simoni | App
H-000030 | 2026-09-24 | 2026-09-24 13:30 | IST-002 | Note | Update |  |  |  | Plant created; pricing conditions pending | T. Simoni | App
H-000031 | 2026-09-22 | 2026-09-22 12:00 | IST-003 | Note | Update |  |  |  | Order confirmed, delivery wk 40 | T. Simoni | App
H-000032 | 2026-09-04 | 2026-09-04 10:00 | KSA-CO-001 | Note | Update |  |  |  | Application filed with MISA | T. Simoni | App
H-000033 | 2026-09-18 | 2026-09-18 17:00 | KSA-CO-001 | Note | Update |  |  |  | Second request for documents from MISA | T. Simoni | App
H-000034 | 2026-09-29 | 2026-09-29 10:42 | AMS-003 | Change |  | Status | In Progress | Blocked |  | T. Simoni | App | SESSION-20260929-001 | Verified
H-000035 | 2026-09-29 | 2026-09-29 10:47 | AMS-003 | Note | Update |  |  |  | Waiting for Schiphol security feedback | T. Simoni | App | SESSION-20260929-001 | Verified
H-000036 | 2026-09-29 | 2026-09-29 10:55 | AMS-006 | Change |  | Decision Required | FALSE | TRUE |  | T. Simoni | App | SESSION-20260929-001 | Verified

## OPENINGS
Opening Code | Opening Type | Location | Country | Complexity | Project Start Date | Opening Status | Related Opening | Baseline Opening Date | Current Opening Date | Delay (wd) | Postponements | Days Elapsed (wd) | Planned Duration (wd) | Days Remaining (wd) | Next Task ID | Check
CZE-CO | New Company | Czech Republic | Czech Republic | Medium | 2026-05-04 | Confirmed | CZE
ARG-CO | New Company | Argentina | Argentina | High | 2026-06-01 | Tentative | ARG
KSA-CO | New Company | Saudi Arabia | Saudi Arabia | High | 2026-03-02 | Confirmed | KSA
HUN-CO | New Company | Hungary | Hungary | Medium | 2026-06-15 | Tentative | HUN
SBH-CO | New Company | Saint Barth | Saint Barthélemy | High | 2026-03-16 | Confirmed | SBH
IST | New Store | Istanbul Airport | Turkey | Medium | 2026-03-02 | Confirmed
COL | New Store | Colombia | Colombia | High | 2026-06-01 | Tentative
ROU | New Store | Romania | Romania | Medium | 2026-05-04 | Tentative
PER | New Store | Peru | Peru | High | 2026-07-01 | Tentative
AMS | New Store | Amsterdam Airport | Netherlands | Medium | 2026-03-01 | Confirmed
KSA | New Store | Saudi Arabia | Saudi Arabia | High | 2026-04-01 | Tentative | KSA-CO
SIN | New Store | Singapore Airport | Singapore | Medium | 2026-04-15 | Confirmed
CZE | New Store | Czech Republic | Czech Republic | Medium | 2026-06-15 | Tentative | CZE-CO
HUN | New Store | Hungary | Hungary | Medium | 2026-07-01 | Tentative | HUN-CO
MAD | New Store | Madrid Airport | Spain | Low | 2026-02-02 | Confirmed
SBH | New Store | Saint Barth | Saint Barthélemy | High | 2026-05-04 | Confirmed | SBH-CO
ARG | New Store | Argentina | Argentina | High | 2026-08-03 | Tentative | ARG-CO
DXB | New Store | Dubai Airport | United Arab Emirates | Medium | 2026-03-16 | Confirmed
URY | New Store | Uruguay | Uruguay | Medium | 2026-09-01 | Tentative

## OPENING_DATE_HISTORY
Change ID | Opening Code | Entry Type | Decided On | New Opening Date | Previous Date | Shift (wd) | Reason | Recorded By | Session ID
OD-001 | CZE-CO | Baseline | 2026-05-04 | 2026-12-15 |  |  | Initial plan | T. Simoni
OD-002 | ARG-CO | Baseline | 2026-06-01 | 2027-02-26 |  |  | Initial plan | T. Simoni
OD-003 | KSA-CO | Baseline | 2026-03-02 | 2026-09-30 |  |  | Initial plan | T. Simoni
OD-004 | HUN-CO | Baseline | 2026-06-15 | 2027-01-29 |  |  | Initial plan | T. Simoni
OD-005 | SBH-CO | Baseline | 2026-03-16 | 2026-10-30 |  |  | Initial plan | T. Simoni
OD-006 | IST | Baseline | 2026-03-02 | 2026-11-20 |  |  | Initial plan | T. Simoni
OD-007 | COL | Baseline | 2026-06-01 | 2027-03-15 |  |  | Initial plan | T. Simoni
OD-008 | ROU | Baseline | 2026-05-04 | 2027-02-10 |  |  | Initial plan | T. Simoni
OD-009 | PER | Baseline | 2026-07-01 | 2027-04-20 |  |  | Initial plan | T. Simoni
OD-010 | AMS | Baseline | 2026-03-01 | 2026-11-30 |  |  | Initial plan | T. Simoni
OD-011 | KSA | Baseline | 2026-04-01 | 2027-01-25 |  |  | Initial plan | T. Simoni
OD-012 | SIN | Baseline | 2026-04-15 | 2026-12-05 |  |  | Initial plan | T. Simoni
OD-013 | CZE | Baseline | 2026-06-15 | 2027-02-26 |  |  | Initial plan | T. Simoni
OD-014 | HUN | Baseline | 2026-07-01 | 2027-03-26 |  |  | Initial plan | T. Simoni
OD-015 | MAD | Baseline | 2026-02-02 | 2026-10-16 |  |  | Initial plan | T. Simoni
OD-016 | SBH | Baseline | 2026-05-04 | 2026-12-18 |  |  | Initial plan | T. Simoni
OD-017 | ARG | Baseline | 2026-08-03 | 2027-05-14 |  |  | Initial plan | T. Simoni
OD-018 | DXB | Baseline | 2026-03-16 | 2026-11-14 |  |  | Initial plan | T. Simoni
OD-019 | URY | Baseline | 2026-09-01 | 2027-06-11 |  |  | Initial plan | T. Simoni
OD-020 | KSA-CO | Change | 2026-05-15 | 2026-10-31 |  |  | Commercial registration delayed | T. Simoni
OD-021 | AMS | Change | 2026-06-12 | 2026-12-15 |  |  | Airport unit handover delayed | T. Simoni | SESSION-20260612-001
OD-022 | MAD | Change | 2026-07-20 | 2026-11-06 |  |  | Landlord works delayed | T. Simoni
OD-023 | DXB | Change | 2026-09-03 | 2026-12-12 |  |  | Duty-free operator agreement pending | T. Simoni
OD-024 | KSA-CO | Change | 2026-09-10 | 2026-11-30 |  |  | MISA license pending | T. Simoni

## SESSIONS
Session ID | Started At | Ended At | Session Type | Openings in Scope | Run By | Changes | Verified | Mismatches | Exported At
SESSION-20260922-001 | 2026-09-22 10:00 | 2026-09-22 11:05 | SAL | AMS, MAD | T. Simoni |  |  |  | 2026-09-22 11:07
SESSION-20260929-001 | 2026-09-29 10:30 | 2026-09-29 11:15 | SAL | AMS, DXB | T. Simoni

## AREAS
Macro Area | Sub Area | Sort Order | Active
Corporate / Legal |  | 1 | TRUE
Contract |  | 2 | TRUE
IT | ERP (SAP) | 3 | TRUE
IT | POS | 4 | TRUE
IT | IT Hardware | 5 | TRUE
IT | CRM | 6 | TRUE
IT | Connectivity | 7 | TRUE
IT | Telephony | 8 | TRUE
Finance & Administration |  | 9 | TRUE
Logistics & Customs |  | 10 | TRUE
Compliance & Labelling |  | 11 | TRUE
HR |  | 12 | TRUE
Store Planning |  | 13 | TRUE
Indirect Materials |  | 14 | TRUE
Allocation & Replenishment |  | 15 | TRUE
General Services |  | 16 | TRUE
Retail |  | 17 | TRUE

## OWNERS
Owner Name | Function | Organisation | Email | Active
T. Simoni | PMO | Golden Goose |  | TRUE
G. Conti | Real Estate | Golden Goose |  | TRUE
C. Villa | Corporate / Legal | Golden Goose |  | TRUE
L. Bianchi | Store Planning | Golden Goose |  | TRUE
S. Moretti | HR | Golden Goose |  | TRUE
M. Ferri | IT | Golden Goose |  | TRUE
A. Greco | Logistics & Customs | Golden Goose |  | TRUE
F. Riva | Compliance & Labelling | Golden Goose |  | TRUE
E. Galli | Finance & Administration | Golden Goose |  | TRUE
D. Serra | Allocation & Replenishment | Golden Goose |  | TRUE
R. Marino | Retail | Golden Goose |  | TRUE
P. Costa | Indirect Materials | Golden Goose |  | TRUE

## LISTS
Status | Progress % | Note Type | Entry Type | Source | Verification | Session Type | Opening Type | Opening Status | Complexity | Date Entry Type | Locations | Macro Areas | Sub Areas | Organisation
Not Started | 0 | Update | Created | App | Verified | SAL | New Store | Tentative | Low | Baseline |  |  |  | Golden Goose
In Progress | 25 | Decision | Snapshot | Sheet | Pending | Review | New Company | Confirmed | Medium | Change |  |  |  | External
Blocked | 50 |  | Note |  | Mismatch | Ad-hoc |  | Opened | High
Completed | 75 |  | Change |  | Error |  |  | Cancelled
N/A | 100 |  |  |  | Superseded